## 표지
Warriors 게임 개발
상세일정계획서
문서번호 :
Ver 1.0

## 재개정이력
상세일정계획서
문 서 정 보
구분 | 직책 |  | 이름 | 일자 | 서명
작성 | Project Manager(PM) |  | 박기석 | 2021.02.07
검토 | Project Manager(PM) |  | 박기석 | 2021.02.07
승인 | Team Leader |  | 강건휘
제·개정 이력
제·개정일 | Version | 제·개정 내용 |  | 개정위치 | 작성자 | 검토자 | 승인자
2021.02.07 | 1 | 최초 작성 |  | 전체 | 박기석 | 박기석 | 강건휘
2021.02.08 | 1.1 | 애니메이션 / 서버 상세일정계획서 업데이트 |  | 상세일정계획서 | 조성민, 박기석 | 박기석 | 강건휘

## 상세일정계획서
[9 empty] | 진척 입력 | [5 empty] | 계획 입력 | 계획 입력 | 입력 | 입력 |  |  | 상세일정계획서
[41 empty] | 중간 평가 | [13 empty] | DEMO 평가 | [14 empty] | 최종 제출
번호 | 단계 | 태스크 |  |  | 담당자 | 결과물 | 가중치 | 시점 계획 완료율 | 시점 실적 완료율 | 시점 가중치 계획 | 시점 가중치 실적 | 시점 편차 | 실적율 | 진행 상태 | 시작계획일 | 종료계획일 | 실제시작일 | 실제종료일 | 선행 태스크No | CP | 작업 기간 | 1주 | 2주 | 3주 | 4주 | 5주 | 6주 | 7주 | 8주 | 9주 | 10주 | 11주 | 12주 | 13주 | 14주 | 15주 | 16주 | 17주 | 18주 | 19주 | 20주 | 21주 | 22주 | 23주 | 24주 | 25주 | 26주 | 27주 | 28주 | 29주 | 30주 | 31주 | 32주 | 33주 | 34주 | 35주 | 36주 | 37주 | 38주 | 39주 | 40주 | 41주 | 42주 | 43주 | 44주 | 45주 | 46주 | 47주 | 48주 | 49주
 | time axis 2020-12-27 to 2021-11-28
 | time axis 2021-01-02 to 2021-12-04
0 | 0 | [6 empty] | 57.86% | 44.39% | 0 | 0 | 0 | 76.72% | 진행 | 2020-06-09 | 2021-08-16 | 2020-06-01 |  |  |  | 310 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | A.0 | 프로젝트 관리 |  |  |  |  | 10 | 54.23% | 34% | 0.054225 | 0.034 | -0.020225 | 62.7% | 지연 | 2020-06-09 | 2021-08-16 | 2020-06-01 |  |  |  | 310 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1 |  | A.0.1 | 착수/계획 |  |  |  | 30 | 100% | 60% | 0.3 | 0.18 | -0.12 | 60% | 지연 | 2020-06-09 | 2021-03-02 | 2020-06-01 |  |  |  | 191 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 |  |  | 프로젝트 수행계획 수립 |  |  |  | 80 | 100% | 75% | 0.8 | 0.6 | -0.2 | 75% | 지연 | 2020-06-09 | 2021-03-02 | 2020-06-01 |  |  |  | 191 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.1.1 |  |  |  | 프로젝트 개발초안 수립 | 박기석 | 데모프로젝트 개발일정, Warriors.pptx | 25 | 100% | 100% | 0.25 | 0.25 | 0 | 100% | 종료 | 2020-06-09 | 2020-12-14 | 2020-06-01 | 2020-12-14 |  |  | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.1.2 |  |  |  | 프로젝트 수행계획 수립 | 박기석 | Warriors_발표자료.pptx | 50 | 100% | 100% | 0.5 | 0.5 | 0 | 100% | 종료 | 2020-12-14 | 2020-12-28 | 2020-12-14 | 2020-12-28 |  |  | 11 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.1.3 |  |  |  | 프로젝트 상세일정 수립 | 박기석 | 주요일정계획서, 상세일정계획서(WBS) | 25 | 100% | 0% | 0.25 | 0 | -0.25 | 0% | 지연 | 2020-12-28 | 2021-02-28 | 2020-12-28 | 2021-03-01 |  |  | 45 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.2 |  |  | 단계 검토 |  |  |  | 20 | 100% | 0% | 0.2 | 0 | -0.2 | 0% | 지연 | 2021-02-14 | 2021-03-02 | 2021-02-14 |  |  |  | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.2.1 |  |  |  | 프로젝트 상세일정 검토 | 전 팀원 | 주요일정계획서, 상세일정계획서(WBS) | 50 | 100% | 0% | 0.5 | 0 | -0.5 | 0% | 지연 | 2021-02-14 | 2021-02-28 | 2021-02-14 |  |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.2.2 |  |  |  | 지도교수 검토 및 승인 | 이택희 |  | 50 | 100% | 0% | 0.5 | 0 | -0.5 | 0% | 지연 | 2021-03-01 | 2021-03-02 |  |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 |  | A.0.2 | 실행 |  |  |  | 40 | 60.56% | 40% | 0.24225 | 0.16 | -0.082254 | 66.05% | 지연 | 2020-12-28 | 2021-08-13 | 2020-12-28 |  |  |  | 165 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.1 |  |  | 보고 |  |  |  | 100 | 60.56% | 40% | 0.60563 | 0.4 | -0.20563 | 66.05% | 지연 | 2020-12-28 | 2021-08-13 | 2020-12-28 |  |  |  | 165 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.1.1 |  |  |  | 계획보고 | 박기석 | Warriors.pptx | 40 | 100% | 100% | 0.4 | 0.4 | 0 | 100% | 종료 | 2020-12-28 | 2020-12-28 | 2020-12-28 | 2020-12-28 |  |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.1.2 |  |  |  | 중간보고 | 박기석 | 중간보고서 | 20 | 100% | 0% | 0.2 | 0 | -0.2 | 0% | 지연 | 2020-12-28 | 2021-05-07 | 2020-12-28 |  |  |  | 95 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.1.3 |  |  |  | 완료보고 | 박기석 | 완료보고서 | 40 | 1.408% | 0% | 0.0056338 | 0 | -0.0056338 | 0% | 지연 | 2021-05-07 | 2021-08-13 |  |  |  |  | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 |  | A.0.3 | 프로젝트 종료 |  |  |  | 30 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-08-13 | 2021-08-16 |  |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.1 |  |  | 프로젝트 종료 |  |  |  | 100 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-08-13 | 2021-08-16 |  |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.1.1 |  |  |  | 최종 프로젝트 확인 |  |  | 100 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-08-13 | 2021-08-16 |  |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | A.1 | 프로젝트 수행 (Graphic) |  |  |  |  | 20 | 63.38% | 52.02% | 0.12676 | 0.10405 | -0.022709 | 82.09% | 지연 | 2020-07-01 | 2021-08-15 | 2020-07-01 |  |  |  | 293 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1 |  | A.1.1 | 캐릭터 |  |  |  | 60 | 100% | 83.38% | 0.6 | 0.50025 | -0.09975 | 83.38% | 지연 | 2020-07-01 | 2021-04-15 | 2020-07-01 |  |  |  | 207 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1 |  |  | 기사 캐릭터 |  |  |  | 50 | 100% | 100% | 0.5 | 0.5 | 0 | 100% | 종료 | 2020-07-01 | 2020-10-31 | 2020-07-01 | 2020-10-31 |  |  | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.1 |  |  |  | 래퍼런스 수집 |  |  | 5 | 100% | 100% | 0.05 | 0.05 | 0 | 100% | 종료 | 2020-07-01 | 2020-07-10 | 2020-07-01 | 2020-07-10 |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.2 |  |  |  | 로우폴리곤 제작 |  |  | 25 | 100% | 100% | 0.25 | 0.25 | 0 | 100% | 종료 | 2020-07-10 | 2020-07-31 | 2020-07-10 | 2020-07-31 |  |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.3 |  |  |  | 하이폴리곤 제작 |  |  | 40 | 100% | 100% | 0.4 | 0.4 | 0 | 100% | 종료 | 2020-08-01 | 2020-09-15 | 2020-08-01 | 2020-09-15 |  |  | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.4 |  |  |  | 무기 제작 |  |  | 5 | 100% | 100% | 0.05 | 0.05 | 0 | 100% | 종료 | 2020-09-15 | 2020-09-30 | 2020-09-15 | 2020-09-30 |  |  | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.5 |  |  |  | UV 언랩 / 텍스처 제작 |  |  | 25 | 100% | 100% | 0.25 | 0.25 | 0 | 100% | 종료 | 2020-10-01 | 2020-10-31 | 2020-10-01 | 2020-10-31 |  |  | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.2 |  |  | 바이킹 캐릭터 |  |  |  | 50 | 100% | 66.75% | 0.5 | 0.33375 | -0.16625 | 66.75% | 지연 | 2020-11-01 | 2021-04-15 | 2020-11-01 |  |  |  | 119 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.2.1 |  |  |  | 래퍼런스 수집 |  |  | 3 | 100% | 100% | 0.03 | 0.03 | 0 | 100% | 종료 | 2020-11-01 | 2020-11-10 | 2020-11-01 | 2020-11-10 |  |  | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.2.2 |  |  |  | 로우폴리곤 제작 |  |  | 17 | 100% | 100% | 0.17 | 0.17 | 0 | 100% | 종료 | 2020-11-10 | 2020-11-30 | 2020-11-10 | 2021-03-16 |  |  | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.2.3 |  |  |  | 하이폴리곤 제작 |  |  | 30 | 100% | 100% | 0.3 | 0.3 | 0 | 100% | 종료 | 2020-12-01 | 2021-01-15 | 2020-12-01 | 2021-01-15 |  |  | 34 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.2.4 |  |  |  | 무기 제작 |  |  | 5 | 100% | 65% | 0.05 | 0.0325 | -0.0175 | 65% | 지연 | 2021-01-16 | 2021-01-31 | 2021-01-16 | 2021-01-31 |  |  | 10 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.2.5 |  |  |  | UV 언랩 / 텍스처 제작 |  |  | 17 | 100% | 50% | 0.17 | 0.085 | -0.085 | 50% | 지연 | 2021-02-01 | 2021-02-28 | 2021-02-01 |  |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.2.6 |  |  |  | 헤어(머리, 수염, 눈썹, 속눈썹) 제작 |  |  | 25 | 100% | 20% | 0.25 | 0.05 | -0.2 | 20% | 지연 | 2021-03-01 | 2021-03-31 | 2021-02-20 |  |  |  | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.2.7 |  |  |  | 헤어 텍스처 제작 |  |  | 3 | 100% | 0% | 0.03 | 0 | -0.03 | 0% | 지연 | 2021-04-01 | 2021-04-15 |  |  |  |  | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2 |  | A.1.2 | 배경 |  |  |  | 40 | 8.448% | 5% | 0.033793 | 0.02 | -0.013793 | 59.18% | 지연 | 2021-04-16 | 2021-08-15 |  |  |  |  | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.1.1 |  |  |  | 래퍼런스 수집 |  |  | 2 | 100% | 100% | 0.02 | 0.02 | 0 | 100% | 종료 | 2021-04-16 | 2021-04-23 | 2021-02-15 | 2021-04-12 |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.1.2 |  |  |  | 레벨 블록아웃 |  |  | 3 | 100% | 100% | 0.03 | 0.03 | 0 | 100% | 종료 | 2021-04-23 | 2021-04-30 | 2021-04-01 | 2021-04-12 |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.1.3 |  |  |  | 배경 애셋 제작 |  |  | 20 | 17.24% | 0% | 0.034483 | 0 | -0.034483 | 0% | 지연 | 2021-05-01 | 2021-06-10 |  |  |  |  | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.1.3 |  |  |  | UV 언랩 / 텍스처 제작 |  |  | 40 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-06-10 | 2021-07-20 |  |  |  |  | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.1.1 |  |  |  | 배경 애셋 배치 |  |  | 10 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-07-21 | 2021-07-31 |  |  |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.1.2 |  |  |  | 라이팅 및 렌더링 환경 조성 |  |  | 25 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-08-01 | 2021-08-15 |  |  |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | A.2 | 프로젝트 수행 (Client) |  |  |  |  | 20 | 73.2% | 40% | 0.14639 | 0.08 | -0.06639 | 54.65% | 지연 | 2021-01-28 | 2021-07-31 | 2021-01-28 |  |  |  | 132 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1 |  | A.2.1 | 캐릭터 동작 |  |  |  | 20 | 100% | 100% | 0.2 | 0.2 | 0 | 100% | 종료 | 2021-01-28 | 2021-03-08 | 2021-01-28 | 2021-04-03 |  |  | 28 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.1 |  |  | 구르기 |  |  |  | 40 | 100% | 100% | 0.4 | 0.4 | 0 | 100% | 종료 | 2021-01-29 | 2021-02-03 | 2021-01-29 | 2021-02-03 |  |  | 4 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.1.1 |  |  |  | 구르기 기능 구현 |  |  | 40 | 100% | 100% | 0.4 | 0.4 | 0 | 100% | 종료 | 2021-01-29 | 2021-01-29 | 2021-01-29 | 2021-01-29 |  |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.1.2 |  |  |  | 애니메이션 삽입 |  |  | 40 | 100% | 100% | 0.4 | 0.4 | 0 | 100% | 종료 | 2021-02-02 | 2021-02-02 | 2021-02-02 | 2021-02-02 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.1.3 |  |  |  | 스테미나 연동 |  |  | 20 | 100% | 100% | 0.2 | 0.2 | 0 | 100% | 종료 | 2021-02-03 | 2021-02-03 | 2021-02-03 | 2021-02-03 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.2 |  |  | 달리기 |  |  |  | 30 | 100% | 100% | 0.3 | 0.3 | 0 | 100% | 종료 | 2021-01-28 | 2021-02-03 | 2021-01-28 | 2021-02-03 |  |  | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.2.1 |  |  |  | 달리기 기능 구현 |  |  | 60 | 100% | 100% | 0.6 | 0.6 | 0 | 100% | 종료 | 2021-01-28 | 2021-01-28 | 2021-01-28 | 2021-01-28 |  |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.2.2 |  |  |  | 스테미나 연동 |  |  | 40 | 100% | 100% | 0.4 | 0.4 | 0 | 100% | 종료 | 2021-02-03 | 2021-02-03 | 2021-02-03 | 2021-02-03 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.3 |  |  | 공격 |  |  |  | 30 | 100% | 100% | 0.3 | 0.3 | 0 | 100% | 종료 | 2021-01-30 | 2021-02-07 | 2021-01-30 | 2021-02-07 |  |  | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.3.1 |  |  |  | 콤보공격 기능 구현 |  |  | 20 | 100% | 100% | 0.2 | 0.2 | 0 | 100% | 종료 | 2021-01-30 | 2021-01-31 | 2021-01-30 | 2021-01-31 |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.3.2 |  |  |  | 애니메이션 삽입 |  |  | 15 | 100% | 100% | 0.15 | 0.15 | 0 | 100% | 종료 | 2021-02-01 | 2021-02-01 | 2021-02-01 | 2021-02-01 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.3.3 |  |  |  | 애니메이션 블렌딩 |  |  | 10 | 100% | 100% | 0.1 | 0.1 | 0 | 100% | 종료 | 2021-02-02 | 2021-02-03 | 2021-02-02 | 2021-02-03 |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.3.4 |  |  |  | 데미지 처리 기능 구현 |  |  | 10 | 100% | 100% | 0.1 | 0.1 | 0 | 100% | 종료 | 2021-02-04 | 2021-02-06 | 2021-02-04 | 2021-02-06 |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.3.5 |  |  |  | 무기와 캐릭터의 충돌체크 구현 |  |  | 15 | 100% | 100% | 0.15 | 0.15 | 0 | 100% | 종료 | 2021-02-04 | 2021-02-05 | 2021-02-04 | 2021-02-05 |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.3.6 |  |  |  | 무기 애니메이션 삽입 |  |  | 20 | 100% | 100% | 0.2 | 0.2 | 0 | 100% | 종료 | 2021-02-06 | 2021-02-06 | 2021-02-06 | 2021-02-06 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.3.7 |  |  |  | 무기 사용 시 스테미너 연동 |  |  | 10 | 100% | 100% | 0.1 | 0.1 | 0 | 100% | 종료 | 2021-02-07 | 2021-02-07 | 2021-02-07 | 2021-02-07 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.4 |  |  | 패링 |  |  |  | 30 | 100% | 44% | 0.3 | 0.132 | -0.168 | 44% | 지연 | 2021-03-01 | 2021-03-08 | 2021-03-27 | 2021-04-03 |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.4.1 |  |  |  | 패링 성공시 반격 애니메이션 삽입 |  |  | 20 | 100% | 20% | 0.2 | 0.04 | -0.16 | 20% | 지연 | 2021-03-01 | 2021-03-02 | 2021-03-22 |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.4.2 |  |  |  | 패링 확정 공격 구현 |  |  | 20 | 100% | 20% | 0.2 | 0.04 | -0.16 | 20% | 지연 | 2021-03-02 | 2021-03-04 | 2021-03-22 |  |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.4.3 |  |  |  | 스테미나 연동 |  |  | 10 | 100% | 20% | 0.1 | 0.02 | -0.08 | 20% | 지연 | 2021-03-04 | 2021-03-04 | 2021-03-22 |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.4.4 |  |  |  | 무기 간의 충돌체크 |  |  | 30 | 100% | 100% | 0.3 | 0.3 | 0 | 100% | 종료 | 2021-03-05 | 2021-03-07 | 2021-03-22 | 2021-03-29 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.4.5 |  |  |  | 패링 되는 타이밍 체크 |  |  | 20 | 100% | 20% | 0.2 | 0.04 | -0.16 | 20% | 지연 | 2021-03-08 | 2021-03-08 | 2021-03-08 |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2 |  | A.2.2 | 캐릭터 상태 |  |  |  | 20 | 100% | 100% | 0.2 | 0.2 | 0 | 100% | 종료 | 2021-01-30 | 2021-03-11 | 2021-01-30 |  |  |  | 29 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2.1 |  |  | 락온 |  |  |  | 50 | 100% | 100% | 0.5 | 0.5 | 0 | 100% | 종료 | 2021-01-30 | 2021-01-30 | 2021-01-30 | 2021-01-30 |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2.1.1 |  |  |  | 락온 기능 구현 |  |  | 100 | 100% | 100% | 1 | 1 | 0 | 100% | 종료 | 2021-01-30 | 2021-01-30 | 2021-01-30 | 2021-01-30 |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2.2 |  |  | 체력 |  |  |  | 30 | 100% | 100% | 0.3 | 0.3 | 0 | 100% | 종료 | 2021-02-04 | 2021-02-04 | 2021-02-04 | 2021-02-04 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2.2.1 |  |  |  | 체력바 UI (임시) |  |  | 20 | 100% | 100% | 0.2 | 0.2 | 0 | 100% | 종료 | 2021-02-04 | 2021-02-04 | 2021-02-04 | 2021-02-04 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2.2.2 |  |  |  | 체력 기능 구현 |  |  | 80 | 100% | 100% | 0.8 | 0.8 | 0 | 100% | 종료 | 2021-02-04 | 2021-02-04 | 2021-02-04 | 2021-02-04 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2.3 |  |  | 스테미나 |  |  |  | 50 | 100% | 100% | 0.5 | 0.5 | 0 | 100% | 종료 | 2021-02-03 | 2021-02-03 | 2021-02-03 | 2021-02-03 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2.3.1 |  |  |  | 스테미나 바 UI(임시) |  |  | 20 | 100% | 100% | 0.2 | 0.2 | 0 | 100% | 종료 | 2021-02-03 | 2021-02-03 | 2021-02-03 | 2021-02-03 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2.3.2 |  |  |  | 스테미나 기능 구현 |  |  | 80 | 100% | 100% | 0.8 | 0.8 | 0 | 100% | 종료 | 2021-02-03 | 2021-02-03 | 2021-02-03 | 2021-02-03 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2.4 |  |  | 피격 |  |  |  | 50 | 100% | 30% | 0.5 | 0.15 | -0.35 | 30% | 지연 | 2021-03-09 | 2021-03-11 |  |  |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2.4.1 |  |  |  | 피격 애니메이션 삽입 |  |  | 30 | 100% | 100% | 0.3 | 0.3 | 0 | 100% | 종료 | 2021-03-09 | 2021-03-10 | 2021-03-09 | 2021-03-10 |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2.4.2 |  |  |  | 피격 시 프레임상 손해 |  |  | 70 | 100% | 0% | 0.7 | 0 | -0.7 | 0% | 지연 | 2021-03-10 | 2021-03-11 | 2021-03-10 |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.3 |  | A.2.3 | 쉐이더 |  |  |  | 60 | 55.33% | 0% | 0.33195 | 0 | -0.33195 | 0% | 지연 | 2021-02-12 | 2021-07-31 |  |  |  |  | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.3.1 |  |  | 머리카락 커스텀 쉐이더 |  |  |  | 30 | 100% | 0% | 0.3 | 0 | -0.3 | 0% | 지연 | 2021-02-12 | 2021-04-17 |  |  |  |  | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.3.1.1 | [6 empty] | 30 | 100% | 0% | 0.3 | 0 | -0.3 | 0% | 지연 | 2021-02-12 | 2021-04-15 |  |  |  |  | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.3.1.2 | [6 empty] | 30 | 100% | 0% | 0.3 | 0 | -0.3 | 0% | 지연 | 2021-02-13 | 2021-04-16 |  |  |  |  | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.3.1.3 | [6 empty] | 40 | 100% | 0% | 0.4 | 0 | -0.4 | 0% | 지연 | 2021-02-14 | 2021-04-17 |  |  |  |  | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.3.2 |  |  | 안구 커스텀 쉐이더 |  |  |  | 30 | 64.57% | 0% | 0.1937 | 0 | -0.1937 | 0% | 지연 | 2021-03-06 | 2021-06-12 |  |  |  |  | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.3.2.1 | [6 empty] | 30 | 65.22% | 0% | 0.19565 | 0 | -0.19565 | 0% | 지연 | 2021-03-06 | 2021-06-10 |  |  |  |  | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.3.2.2 | [6 empty] | 30 | 64.29% | 0% | 0.19286 | 0 | -0.19286 | 0% | 지연 | 2021-03-07 | 2021-06-11 |  |  |  |  | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.3.2.3 | [6 empty] | 40 | 64.29% | 0% | 0.25714 | 0 | -0.25714 | 0% | 지연 | 2021-03-08 | 2021-06-12 |  |  |  |  | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.3.3 |  |  | 피부 커스텀 쉐이더 |  |  |  | 40 | 14.89% | 0% | 0.059557 | 0 | -0.059557 | 0% | 지연 | 2021-04-23 | 2021-07-31 |  |  |  |  | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.3.3.1 | [6 empty] | 50 | 15.49% | 0% | 0.077465 | 0 | -0.077465 | 0% | 지연 | 2021-04-23 | 2021-07-30 |  |  |  |  | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.3.3.2 | [6 empty] | 50 | 14.29% | 0% | 0.071429 | 0 | -0.071429 | 0% | 지연 | 2021-04-24 | 2021-07-31 |  |  |  |  | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | A.3 | 프로젝트 수행 (Server) |  |  |  |  | 20 | 61.25% | 68.12% | 0.1225 | 0.13625 | 0.01375 | 111.2% | 진행 | 2021-01-26 | 2021-07-12 | 2021-01-26 |  |  |  | 120 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1 |  | A.3.1 | 클라이언트 기능 동기화 |  |  |  | 25 | 100% | 87.5% | 0.25 | 0.21875 | -0.03125 | 87.5% | 지연 | 2021-03-28 | 2021-04-30 | 2021-01-26 | 2021-04-30 |  |  | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.1 |  |  | 위치(Position) |  |  |  | 25 | 100% | 100% | 0.25 | 0.25 | 0 | 100% | 종료 | 2021-03-28 | 2021-04-30 | 2021-03-28 | 2021-04-30 |  |  | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.1.1 |  |  |  | Menu Conversion |  |  | 50 | 100% | 100% | 0.5 | 0.5 | 0 | 100% | 종료 | 2021-04-20 | 2021-04-30 | 2021-04-20 | 2021-04-26 |  |  | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.1.2 |  |  |  | World Position |  |  | 50 | 100% | 100% | 0.5 | 0.5 | 0 | 100% | 종료 | 2021-03-28 | 2021-03-31 | 2021-03-28 | 2021-03-31 |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2 |  |  | 플레이어 정보(PlayerInfo) |  |  |  | 25 | 100% | 100% | 0.25 | 0.25 | 0 | 100% | 종료 | 2021-03-31 | 2021-04-05 | 2021-03-31 | 2021-04-04 |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2.1 |  |  |  | Health Point |  |  | 20 | 100% | 100% | 0.2 | 0.2 | 0 | 100% | 종료 | 2021-03-31 | 2021-04-03 | 2021-03-31 | 2021-04-02 |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2.2 |  |  |  | Stemina |  |  | 20 | 100% | 100% | 0.2 | 0.2 | 0 | 100% | 종료 | 2021-03-31 | 2021-04-03 | 2021-03-31 | 2021-04-02 |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2.3 |  |  |  | Player Name |  |  | 20 | 100% | 100% | 0.2 | 0.2 | 0 | 100% | 종료 | 2021-04-03 | 2021-04-05 | 2021-04-03 | 2021-04-04 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2.4 |  |  |  | Player Image |  |  | 5 | 100% | 100% | 0.05 | 0.05 | 0 | 100% | 종료 | 2021-04-03 | 2021-04-05 | 2021-04-03 | 2021-04-04 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2.5 |  |  |  | Player Status |  |  | 15 | 100% | 100% | 0.15 | 0.15 | 0 | 100% | 종료 | 2021-04-03 | 2021-04-05 | 2021-04-03 | 2021-04-04 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2.6 |  |  |  | Player Character |  |  | 20 | 100% | 100% | 0.2 | 0.2 | 0 | 100% | 종료 | 2021-04-03 | 2021-04-05 | 2021-04-03 | 2021-04-04 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.3 |  |  | 애니메이션 재생 |  |  |  | 25 | 100% | 100% | 0.25 | 0.25 | 0 | 100% | 종료 | 2021-04-05 | 2021-04-20 | 2021-04-05 | 2021-04-20 |  |  | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.3.1 |  |  |  | Moving |  |  | 40 | 100% | 100% | 0.4 | 0.4 | 0 | 100% | 종료 | 2021-04-05 | 2021-04-10 | 2021-04-05 | 2021-04-10 |  |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.3.2 |  |  |  | Attacking |  |  | 40 | 100% | 100% | 0.4 | 0.4 | 0 | 100% | 종료 | 2021-04-10 | 2021-04-15 | 2021-04-10 |  |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.3.3 |  |  |  | Guarding |  |  | 20 | 100% | 100% | 0.2 | 0.2 | 0 | 100% | 종료 | 2021-04-15 | 2021-04-20 | 2021-04-15 |  |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.4 |  |  | 캐릭터 선택 |  |  |  | 25 | 100% | 50% | 0.25 | 0.125 | -0.125 | 50% | 지연 | 2021-04-20 | 2021-04-25 | 2021-04-20 | 2021-02-05 |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.4.1 |  |  |  | Knight |  |  | 50 | 100% | 100% | 0.5 | 0.5 | 0 | 100% | 종료 | 2021-04-20 | 2021-04-23 | 2021-04-20 | 2021-04-23 |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.4.2 |  |  |  | Viking |  |  | 50 | 100% | 0% | 0.5 | 0 | -0.5 | 0% | 지연 | 2021-04-23 | 2021-04-25 | 2021-04-23 |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2 |  | A.3.2 | 서버 기능 |  |  |  | 25 | 100% | 100% | 0.25 | 0.25 | 0 | 100% | 종료 | 2021-01-26 | 2021-04-20 | 2021-01-26 | 2021-04-20 |  |  | 61 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.1 |  |  | Main Menu |  |  |  | 20 | 100% | 100% | 0.2 | 0.2 | 0 | 100% | 종료 | 2021-01-26 | 2021-02-06 | 2021-01-26 | 2021-01-28 |  |  | 9 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.1.1 |  |  |  | UI |  |  | 25 | 100% | 100% | 0.25 | 0.25 | 0 | 100% | 종료 | 2021-01-26 | 2021-01-31 | 2021-01-26 | 2021-01-31 |  |  | 4 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.1.2 |  |  |  | Game Instance |  |  | 40 | 100% | 100% | 0.4 | 0.4 | 0 | 100% | 종료 | 2021-01-31 | 2021-02-03 | 2021-01-31 | 2021-02-03 |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.1.3 |  |  |  | Option |  |  | 20 | 100% | 100% | 0.2 | 0.2 | 0 | 100% | 종료 | 2021-02-03 | 2021-02-05 | 2021-02-03 | 2021-02-04 |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.1.4 |  |  |  | Quit |  |  | 15 | 100% | 100% | 0.15 | 0.15 | 0 | 100% | 종료 | 2021-02-05 | 2021-02-06 | 2021-02-05 | 2021-02-06 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.2 |  |  | Host Menu |  |  |  | 30 | 100% | 100% | 0.3 | 0.3 | 0 | 100% | 종료 | 2021-02-06 | 2021-02-26 | 2021-02-06 | 2021-02-26 |  |  | 15 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.2.1 |  |  |  | UI |  |  | 15 | 100% | 100% | 0.15 | 0.15 | 0 | 100% | 종료 | 2021-02-06 | 2021-02-10 | 2021-02-06 | 2021-02-10 |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.2.2 |  |  |  | Server Name |  |  | 15 | 100% | 100% | 0.15 | 0.15 | 0 | 100% | 종료 | 2021-02-10 | 2021-02-14 | 2021-02-10 | 2021-02-13 |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.2.3 |  |  |  | Create Session |  |  | 20 | 100% | 100% | 0.2 | 0.2 | 0 | 100% | 종료 | 2021-02-14 | 2021-02-20 | 2021-02-14 | 2021-02-20 |  |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.2.4 |  |  |  | LAN |  |  | 25 | 100% | 100% | 0.25 | 0.25 | 0 | 100% | 종료 | 2021-02-20 | 2021-02-23 | 2021-02-20 | 2021-02-23 |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.2.5 |  |  |  | Internet |  |  | 25 | 100% | 100% | 0.25 | 0.25 | 0 | 100% | 종료 | 2021-02-23 | 2021-02-26 | 2021-02-23 | 2021-02-26 |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.3 |  |  | Find a Match Menu |  |  |  | 30 | 100% | 100% | 0.3 | 0.3 | 0 | 100% | 종료 | 2021-02-26 | 2021-03-21 | 2021-02-26 | 2021-03-21 |  |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.3.1 |  |  |  | UI |  |  | 10 | 100% | 100% | 0.1 | 0.1 | 0 | 100% | 종료 | 2021-02-26 | 2021-03-01 | 2021-02-26 | 2021-03-01 |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.3.2 |  |  |  | Quick Match |  |  | 20 | 100% | 100% | 0.2 | 0.2 | 0 | 100% | 종료 | 2021-03-01 | 2021-03-05 | 2021-03-01 | 2021-03-05 |  |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.3.3 |  |  |  | Select Match |  |  | 20 | 100% | 100% | 0.2 | 0.2 | 0 | 100% | 종료 | 2021-03-05 | 2021-03-10 | 2021-03-05 | 2021-03-10 |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.3.4 |  |  |  | Find Session |  |  | 20 | 100% | 100% | 0.2 | 0.2 | 0 | 100% | 종료 | 2021-03-10 | 2021-03-15 | 2021-03-10 | 2021-03-15 |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.3.5 |  |  |  | LAN |  |  | 15 | 100% | 100% | 0.15 | 0.15 | 0 | 100% | 종료 | 2021-03-15 | 2021-03-18 | 2021-03-15 | 2021-03-18 |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.3.6 |  |  |  | Internet |  |  | 15 | 100% | 100% | 0.15 | 0.15 | 0 | 100% | 종료 | 2021-03-18 | 2021-03-21 | 2021-03-18 | 2021-03-21 |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.4 |  |  | Lobby Menu |  |  |  | 20 | 100% | 100% | 0.2 | 0.2 | 0 | 100% | 종료 | 2021-03-21 | 2021-04-20 | 2021-03-21 | 2021-04-20 |  |  | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.4.1 |  |  |  | UI |  |  | 15 | 100% | 100% | 0.15 | 0.15 | 0 | 100% | 종료 | 2021-03-21 | 2021-03-28 | 2021-03-21 | 2021-03-28 |  |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.4.2 |  |  |  | In Game |  |  | 25 | 100% | 100% | 0.25 | 0.25 | 0 | 100% | 종료 | 2021-03-28 | 2021-04-03 | 2021-03-28 | 2021-04-03 |  |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.4.3 |  |  |  | Map / Game Time Select |  |  | 10 | 100% | 100% | 0.1 | 0.1 | 0 | 100% | 종료 | 2021-04-03 | 2021-04-07 | 2021-04-03 | 2021-04-07 |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.4.4 |  |  |  | Character Select |  |  | 20 | 100% | 100% | 0.2 | 0.2 | 0 | 100% | 종료 | 2021-04-07 | 2021-04-10 | 2021-04-07 | 2021-04-10 |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.4.5 |  |  |  | Kick Player |  |  | 10 | 100% | 100% | 0.1 | 0.1 | 0 | 100% | 종료 | 2021-04-10 | 2021-04-15 | 2021-04-10 | 2021-04-15 |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.4.6 |  |  |  | Chat |  |  | 20 | 100% | 100% | 0.2 | 0.2 | 0 | 100% | 종료 | 2021-04-15 | 2021-04-20 | 2021-04-15 | 2021-04-20 |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3 |  | A.3.3 | Steam 연동 |  |  |  | 25 | 45% | 85% | 0.1125 | 0.2125 | 0.1 | 188.9% | 진행 | 2021-04-20 | 2021-05-14 | 2021-03-01 |  |  |  | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.1 |  |  | Steam Server 연동 |  |  |  | 50 | 60% | 70% | 0.3 | 0.35 | 0.05 | 116.7% | 진행 | 2021-04-20 | 2021-05-12 | 2021-04-20 | 2021-05-12 |  |  | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.1.1 |  |  |  | Create Session |  |  | 20 | 100% | 100% | 0.2 | 0.2 | 0 | 100% | 종료 | 2021-04-20 | 2021-04-24 | 2021-04-20 | 2021-04-24 |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.1.2 |  |  |  | Find Session |  |  | 20 | 100% | 100% | 0.2 | 0.2 | 0 | 100% | 종료 | 2021-04-24 | 2021-04-28 | 2021-04-24 | 2021-04-28 |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.1.3 |  |  |  | Kick Player |  |  | 10 | 100% | 100% | 0.1 | 0.1 | 0 | 100% | 종료 | 2021-04-28 | 2021-05-02 | 2021-04-28 | 2021-05-02 |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.1.4 |  |  |  | Chat |  |  | 10 | 100% | 100% | 0.1 | 0.1 | 0 | 100% | 종료 | 2021-05-02 | 2021-05-06 | 2021-05-02 | 2021-05-06 |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.1.5 |  |  |  | Hand Over Ingame |  |  | 10 | 40% | 100% | 0.04 | 0.1 | 0.06 | 250% | 종료 | 2021-05-06 | 2021-05-12 | 2021-05-06 | 2021-05-12 |  |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.1.6 | [6 empty] | 30 | 100% | 0% | 0.3 | 0 | -0.3 | 0% | 지연 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.2 |  |  | Steam 정보 등기화 |  |  |  | 50 | 30% | 100% | 0.15 | 0.5 | 0.35 | 333.3% | 종료 | 2021-05-05 | 2021-05-14 |  |  |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.2.1 |  |  |  | Self Info Display |  |  | 30 | 100% | 100% | 0.3 | 0.3 | 0 | 100% | 종료 | 2021-05-05 | 2021-05-08 | 2021-05-05 | 2021-05-08 |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.2.2 |  |  |  | Friends Info Display |  |  | 40 | 0% | 100% | 0 | 0.4 | 0.4 | 100% | 종료 | 2021-05-08 | 2021-05-11 | 2021-05-08 | 2021-05-11 |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3.2.3 |  |  |  | Opposite Info Display |  |  | 30 | 0% | 100% | 0 | 0.3 | 0.3 | 100% | 종료 | 2021-05-11 | 2021-05-14 | 2021-05-11 | 2021-05-14 |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4 |  | A.3.4 | 서버 최적화 알고리즘 |  |  |  | 25 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-05-14 | 2021-07-12 |  |  |  |  | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4.1 |  |  | Dead Reckoning |  |  |  | 50 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-05-14 | 2021-07-05 |  |  |  |  | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4.1.1 | [6 empty] | 10 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-05-14 | 2021-06-30 |  |  |  |  | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4.1.2 | [6 empty] | 10 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-05-15 | 2021-07-01 |  |  |  |  | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4.1.3 | [6 empty] | 10 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-05-16 | 2021-07-02 |  |  |  |  | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4.1.4 | [6 empty] | 10 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-05-17 | 2021-07-03 |  |  |  |  | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4.1.5 | [6 empty] | 10 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-05-18 | 2021-07-04 |  |  |  |  | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4.1.6 | [6 empty] | 50 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-05-19 | 2021-07-05 |  |  |  |  | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4.2 |  |  | IOCP |  |  |  | 50 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-05-20 | 2021-07-12 |  |  |  |  | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4.2.1 | [6 empty] | 10 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-05-20 | 2021-07-06 |  |  |  |  | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4.2.2 | [6 empty] | 10 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-05-21 | 2021-07-07 |  |  |  |  | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4.2.3 | [6 empty] | 10 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-05-22 | 2021-07-08 |  |  |  |  | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4.2.4 | [6 empty] | 10 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-05-23 | 2021-07-09 |  |  |  |  | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4.2.5 | [6 empty] | 10 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-05-24 | 2021-07-10 |  |  |  |  | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4.2.6 | [6 empty] | 10 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-05-25 | 2021-07-11 |  |  |  |  | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4.2.7 | [6 empty] | 40 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-05-26 | 2021-07-12 |  |  |  |  | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | A.4 | 프로젝트 수행 (Animation) |  |  |  |  | 20 | 64.37% | 44.8% | 0.12875 | 0.0896 | -0.039149 | 69.59% | 지연 | 2020-08-01 | 2021-08-14 | 2020-08-01 |  |  |  | 270 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1 |  | A.4.1 | 리깅 |  |  |  | 40 | 100% | 50% | 0.4 | 0.2 | -0.2 | 50% | 지연 | 2020-08-01 | 2021-03-31 | 2020-08-01 |  |  |  | 173 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1.1 |  |  | 기사 리깅 |  |  |  | 50 | 100% | 100% | 0.5 | 0.5 | 0 | 100% | 종료 | 2020-08-01 | 2020-08-31 | 2020-08-01 | 2020-08-31 | 2.1.1.5 | #VALUE! | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1.1.1 | [6 empty] | 20 | 100% | 100% | 0.2 | 0.2 | 0 | 100% | 종료 | 2020-08-01 | 2020-08-31 | 2020-08-01 | 2020-08-31 |  |  | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1.1.2 | [6 empty] | 20 | 100% | 100% | 0.2 | 0.2 | 0 | 100% | 종료 | 2020-08-01 | 2020-08-31 | 2020-08-01 | 2020-08-31 |  |  | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1.1.3 | [6 empty] | 20 | 100% | 100% | 0.2 | 0.2 | 0 | 100% | 종료 | 2020-08-01 | 2020-08-31 | 2020-08-01 | 2020-08-31 |  |  | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1.1.4 | [6 empty] | 20 | 100% | 100% | 0.2 | 0.2 | 0 | 100% | 종료 | 2020-08-01 | 2020-08-31 | 2020-08-01 | 2020-08-31 |  |  | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1.1.5 | [6 empty] | 20 | 100% | 100% | 0.2 | 0.2 | 0 | 100% | 종료 | 2020-08-01 | 2020-08-31 | 2020-08-01 | 2020-08-31 |  |  | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1.2 |  |  | 바이킹 리깅 |  |  |  | 50 | 100% | 0% | 0.5 | 0 | -0.5 | 0% | 지연 | 2021-03-01 | 2021-03-31 |  |  | 2.1.2.5 | #VALUE! | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1.2.1 | [6 empty] | 40 | 100% | 0% | 0.4 | 0 | -0.4 | 0% | 지연 | 2021-03-01 | 2021-03-31 |  |  |  |  | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1.2.2 | [6 empty] | 20 | 100% | 0% | 0.2 | 0 | -0.2 | 0% | 지연 | 2021-03-01 | 2021-03-31 |  |  |  |  | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1.2.3 | [6 empty] | 20 | 100% | 0% | 0.2 | 0 | -0.2 | 0% | 지연 | 2021-03-01 | 2021-03-31 |  |  |  |  | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1.2.4 | [6 empty] | 20 | 100% | 0% | 0.2 | 0 | -0.2 | 0% | 지연 | 2021-03-01 | 2021-03-31 |  |  |  |  | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2 |  | A.4.2 | 애니메이션 |  |  |  | 40 | 60.94% | 50% | 0.24374 | 0.2 | -0.043745 | 82.05% | 지연 | 2020-09-01 | 2021-03-20 | 2020-09-01 |  |  |  | 144 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.1 |  |  | 기사 캐릭터 |  |  |  | 50 | 100% | 100% | 0.5 | 0.5 | 0 | 100% | 종료 | 2020-09-01 | 2021-03-18 | 2020-09-01 | 2021-03-22 |  |  | 143 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.1.1 |  |  |  | Move W |  |  | 2.5 | 100% | 100% | 0.025 | 0.025 | 0 | 100% | 종료 | 2020-09-01 | 2020-09-30 | 2020-09-01 | 2020-09-25 |  |  | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.1.2 |  |  |  | Move D |  |  | 2.5 | 100% | 100% | 0.025 | 0.025 | 0 | 100% | 종료 | 2020-09-01 | 2020-09-30 | 2020-09-01 | 2020-09-25 |  |  | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.1.3 |  |  |  | Move A |  |  | 2.5 | 100% | 100% | 0.025 | 0.025 | 0 | 100% | 종료 | 2020-09-01 | 2020-09-30 | 2020-09-01 | 2020-09-25 |  |  | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.1.4 |  |  |  | Move S |  |  | 2.5 | 100% | 100% | 0.025 | 0.025 | 0 | 100% | 종료 | 2020-09-01 | 2020-09-30 | 2020-09-01 | 2020-10-05 |  |  | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.1.5 |  |  |  | Attack |  |  | 2.5 | 100% | 100% | 0.025 | 0.025 | 0 | 100% | 종료 | 2020-10-10 | 2020-10-30 | 2020-10-01 | 2020-10-18 |  |  | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.1.6 |  |  |  | Focus Idle |  |  | 2.5 | 100% | 100% | 0.025 | 0.025 | 0 | 100% | 종료 | 2020-09-10 | 2020-09-30 | 2020-09-15 | 2020-09-25 |  |  | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.1.7 |  |  |  | Focus Idle to Focus |  |  | 2.5 | 100% | 100% | 0.025 | 0.025 | 0 | 100% | 종료 | 2021-01-20 | 2021-02-10 | 2021-01-20 | 2021-02-02 |  |  | 16 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.1.8 |  |  |  | Guard to Idle |  |  | 2.5 | 100% | 100% | 0.025 | 0.025 | 0 | 100% | 종료 | 2021-02-10 | 2021-03-10 | 2021-02-10 | 2021-03-10 |  |  | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.1.9 |  |  |  | Forward Roll |  |  | 2.5 | 100% | 100% | 0.025 | 0.025 | 0 | 100% | 종료 | 2020-09-15 | 2020-09-30 | 2020-09-15 | 2020-09-26 |  |  | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.1.10 |  |  |  | Guard Breaked |  |  | 5 | 100% | 100% | 0.05 | 0.05 | 0 | 100% | 종료 | 2021-02-01 | 2021-02-28 | 2021-02-01 | 2021-02-13 |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.1.11 |  |  |  | Guard Be Hit |  |  | 5 | 100% | 100% | 0.05 | 0.05 | 0 | 100% | 종료 | 2021-02-01 | 2021-02-15 | 2021-02-01 | 2021-02-11 |  |  | 11 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.1.12 |  |  |  | Groggy |  |  | 5 | 100% | 100% | 0.05 | 0.05 | 0 | 100% | 종료 | 2021-02-01 | 2021-02-28 | 2021-02-01 | 2021-02-13 |  |  | 20
5.2.1.13 |  |  |  | Groggy to Idle |  |  | 5 | 100% | 100% | 0.05 | 0.05 | 0 | 100% | 종료 | 2021-02-01 | 2021-02-28 | 2021-02-01 | 2021-02-14 |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.1.14 |  |  |  | Guard Idle |  |  | 5 | 100% | 100% | 0.05 | 0.05 | 0 | 100% | 종료 | 2021-02-10 | 2021-02-28 | 2021-02-01 | 2021-02-10 |  |  | 13
5.2.1.15 |  |  |  | Be Hit |  |  | 5 | 100% | 100% | 0.05 | 0.05 | 0 | 100% | 종료 | 2021-02-12 | 2021-02-28 | 2021-02-12 | 2021-02-14 |  |  | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.1.16 |  |  |  | Idle to Focus Idle |  |  | 5 | 100% | 100% | 0.05 | 0.05 | 0 | 100% | 종료 | 2020-11-01 | 2020-11-20 | 2020-11-01 | 2020-11-11 |  |  | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.1.17 |  |  |  | Idle to Guard |  |  | 10 | 100% | 100% | 0.1 | 0.1 | 0 | 100% | 종료 | 2021-02-01 | 2021-02-20 | 2021-02-01 | 2021-02-09 |  |  | 15 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.1.18 |  |  |  | Run |  |  | 2.5 | 100% | 100% | 0.025 | 0.025 | 0 | 100% | 종료 | 2020-09-10 | 2020-09-30 | 2021-09-10 | 2021-09-25 |  |  | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.1.19 |  |  |  | Run Attack |  |  | 10 | 100% | 100% | 0.1 | 0.1 | 0 | 100% | 종료 | 2021-01-20 | 2021-02-15 | 2021-01-20 | 2021-02-06 |  |  | 19 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.1.20 |  |  |  | Dead |  |  | 2.5 | 100% | 100% | 0.025 | 0.025 | 0 | 100% | 종료 | 2021-02-10 | 2021-03-10 | 2021-02-10 | 2021-02-24 |  |  | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.1.21 |  |  |  | Special Attack |  |  | 2.5 | 100% | 100% | 0.025 | 0.025 | 0 | 100% | 종료 | 2021-02-10 | 2021-03-10 | 2021-02-10 | 2021-03-10 |  |  | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.1.22 |  |  |  | Be Hit Groggy |  |  | 2.5 | 100% | 100% | 0.025 | 0.025 | 0 | 100% | 종료 | 2021-02-10 | 2021-03-12 | 2021-02-10 | 2021-03-12 |  |  | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.1.23 |  |  |  | Punish |  |  | 2.5 | 100% | 100% | 0.025 | 0.025 | 0 | 100% | 종료 | 2021-02-10 | 2021-03-14 | 2021-02-10 | 2021-03-14 |  |  | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.1.24 |  |  |  | Special Init |  |  | 2.5 | 100% | 100% | 0.025 | 0.025 | 0 | 100% | 종료 | 2021-02-10 | 2021-03-16 | 2021-02-10 | 2021-03-16 |  |  | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.1.25 |  |  |  | Special Be Hit |  |  | 2.5 | 100% | 100% | 0.025 | 0.025 | 0 | 100% | 종료 | 2021-02-10 | 2021-03-18 | 2021-02-10 | 2021-03-20 |  |  | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.1.26 |  |  |  | Be Punished |  |  | 2.5 | 100% | 100% | 0.025 | 0.025 | 0 | 100% | 종료 | 2021-02-10 | 2021-03-20 | 2021-02-10 | 2021-03-22 |  |  | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.1.27 |  |  |  | Idle |  |  | 2.5 | 100% | 100% | 0.025 | 0.025 | 0 | 100% | 종료 | 2021-02-10 | 2021-03-20 | 2021-02-10 | 2021-03-22 |  |  | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.2 |  |  | 바이킹 캐릭터 |  |  |  | 50 | 21.87% | 0% | 0.10936 | 0 | -0.10936 | 0% | 지연 | 2021-03-15 | 2021-08-06 |  |  |  |  | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.2.1 |  |  |  | Move W |  |  | 2.5 | 100% | 0% | 0.025 | 0 | -0.025 | 0% | 지연 | 2021-03-15 | 2021-04-15 |  |  |  |  | 24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5.2.2.2 |  |  |  | Move D |  |  | 2.5 | 100% | 0% | 0.025 | 0 | -0.025 | 0% | 지연 | 2021-03-15 | 2021-04-15 |  |  |  |  | 24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5.2.2.3 |  |  |  | Move A |  |  | 2.5 | 100% | 0% | 0.025 | 0 | -0.025 | 0% | 지연 | 2021-03-15 | 2021-04-15 |  |  |  |  | 24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5.2.2.4 |  |  |  | Move S |  |  | 2.5 | 100% | 0% | 0.025 | 0 | -0.025 | 0% | 지연 | 2021-03-15 | 2021-04-15 |  |  |  |  | 24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5.2.2.5 |  |  |  | Attack |  |  | 2.5 | 50% | 0% | 0.0125 | 0 | -0.0125 | 0% | 지연 | 2021-05-01 | 2021-05-15 |  |  |  |  | 10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5.2.2.6 |  |  |  | Focus Idle |  |  | 2.5 | 100% | 0% | 0.025 | 0 | -0.025 | 0% | 지연 | 2021-04-01 | 2021-04-15 |  |  |  |  | 11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5.2.2.7 |  |  |  | Focus Idle to Focus |  |  | 2.5 | 100% | 0% | 0.025 | 0 | -0.025 | 0% | 지연 | 2021-03-15 | 2021-04-15 |  |  |  |  | 24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5.2.2.8 |  |  |  | Guard to Idle |  |  | 2.5 | 100% | 0% | 0.025 | 0 | -0.025 | 0% | 지연 | 2021-04-01 | 2021-04-15 |  |  |  |  | 11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5.2.2.9 |  |  |  | Forward Roll |  |  | 2.5 | 77.27% | 0% | 0.019318 | 0 | -0.019318 | 0% | 지연 | 2021-04-15 | 2021-05-15 |  |  |  |  | 22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5.2.2.10 |  |  |  | Guard Breaked |  |  | 5 | 23.81% | 0% | 0.011905 | 0 | -0.011905 | 0% | 지연 | 2021-05-01 | 2021-05-31 |  |  |  |  | 21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5.2.2.11 |  |  |  | Guard Be Hit |  |  | 5 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-05-15 | 2021-06-15 |  |  |  |  | 22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5.2.2.12 |  |  |  | Groggy |  |  | 5 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-05-15 | 2021-06-15 |  |  |  |  | 22
5.2.2.13 |  |  |  | Groggy to Idle |  |  | 5 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-06-01 | 2021-06-20 |  |  |  |  | 14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5.2.2.14 |  |  |  | Guard Idle |  |  | 5 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-06-01 | 2021-06-20 |  |  |  |  | 14
5.2.2.15 |  |  |  | Be Hit |  |  | 5 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-06-10 | 2021-06-30 |  |  |  |  | 15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5.2.2.16 |  |  |  | Idle to Focus Idle |  |  | 5 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-07-01 | 2021-07-31 |  |  |  |  | 22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5.2.2.17 |  |  |  | Idle to Guard |  |  | 10 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-07-02 | 2021-08-01 |  |  |  |  | 21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5.2.2.18 |  |  |  | Run |  |  | 2.5 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-07-03 | 2021-08-02 |  |  |  |  | 21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5.2.2.19 |  |  |  | Run Attack |  |  | 10 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-07-10 | 2021-07-31 |  |  |  |  | 15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5.2.2.20 |  |  |  | Dead |  |  | 2.5 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-07-11 | 2021-08-01 |  |  |  |  | 15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5.2.2.21 |  |  |  | Special Attack |  |  | 2.5 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-07-12 | 2021-08-02 |  |  |  |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.2.22 |  |  |  | Be Hit Groggy |  |  | 2.5 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-07-13 | 2021-08-03 |  |  |  |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.2.23 |  |  |  | Punish |  |  | 2.5 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-07-14 | 2021-08-04 |  |  |  |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.2.24 |  |  |  | Special Init |  |  | 2.5 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-07-15 | 2021-08-05 |  |  |  |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.2.25 |  |  |  | Special Be Hit |  |  | 2.5 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-07-16 | 2021-08-06 |  |  |  |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.2.26 |  |  |  | Be Punished |  |  | 2.5 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-07-17 | 2021-08-07 |  |  |  |  | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.2.26 |  |  |  | Idle |  |  | 2.5 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-07-17 | 2021-08-07 |  |  |  |  | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.3 |  | A.4.3 | 이펙트 |  |  |  | 20 | 0% | 24% | 0 | 0.048 | 0.048 | 24% | 진행 | 2021-07-01 | 2021-08-14 |  |  |  |  | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.3.1 |  |  | 검기 |  |  |  | 30 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-07-01 | 2021-08-04 |  |  |  |  | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.3.1.1 | [6 empty] | 20 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-07-01 | 2021-07-31 |  |  |  |  | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.3.1.2 | [6 empty] | 20 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-07-02 | 2021-08-01 |  |  |  |  | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.3.1.3 | [6 empty] | 20 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-07-03 | 2021-08-02 |  |  |  |  | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.3.1.4 | [6 empty] | 20 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-07-04 | 2021-08-03 |  |  |  |  | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.3.1.5 | [6 empty] | 20 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-07-05 | 2021-08-04 |  |  |  |  | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.3.2 |  |  | 스파크 |  |  |  | 30 | 0% | 40% | 0 | 0.12 | 0.12 | 40% | 진행 | 2021-07-10 | 2021-08-13 |  |  |  |  | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.3.2.1 |  |  |  | Sword |  |  | 40 | 0% | 100% | 0 | 0.4 | 0.4 | 100% | 종료 | 2021-07-10 | 2021-08-10 | 2021-03-22 | 2021-03-25 |  |  | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.3.2.2 | [6 empty] | 20 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-07-11 | 2021-08-11 |  |  |  |  | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.3.2.3 | [6 empty] | 20 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-07-12 | 2021-08-12 |  |  |  |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.3.2.4 | [6 empty] | 20 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-07-13 | 2021-08-13 |  |  |  |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.3.3 |  |  | 먼지 |  |  |  | 20 | 0% | 60% | 0 | 0.12 | 0.12 | 60% | 진행 | 2021-07-15 | 2021-08-14 |  |  |  |  | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.3.3.1 |  |  |  | Foot Dust |  |  | 40 | 0% | 100% | 0 | 0.4 | 0.4 | 100% | 종료 | 2021-07-15 | 2021-08-11 | 2021-03-25 | 2021-03-29 |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.3.3.2 |  |  |  | Contact Dust |  |  | 20 | 0% | 100% | 0 | 0.2 | 0.2 | 100% | 종료 | 2021-07-16 | 2021-08-12 | 2021-03-29 | 2021-04-03 |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.3.3.3 | [6 empty] | 20 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-07-17 | 2021-08-13 |  |  |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.3.3.4 | [6 empty] | 20 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-07-18 | 2021-08-14 |  |  |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.3.4 |  |  | 피 |  |  |  | 20 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-07-15 | 2021-08-14 |  |  |  |  | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.3.4.1 | [6 empty] | 40 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-07-15 | 2021-08-11 |  |  |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.3.4.2 | [6 empty] | 20 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-07-16 | 2021-08-12 |  |  |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.3.4.3 | [6 empty] | 20 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-07-17 | 2021-08-13 |  |  |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.3.4.4 | [6 empty] | 20 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-07-18 | 2021-08-14 |  |  |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | A.5 | 테스트 |  |  |  |  | 10 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-08-10 | 2021-08-15 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1 |  | A.5.1 | 통합테스트 |  |  |  | 100 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-08-10 | 2021-08-15 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1.1 |  |  | 통합테스트 계획 |  |  |  | 20 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-08-10 | 2021-08-14 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1.1.1 | [6 empty] | 100 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-08-10 | 2021-08-14 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1.2 |  |  | 통합테스트 |  |  |  | 50 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-08-14 | 2021-08-14 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1.2.1 | [6 empty] | 100 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-08-14 | 2021-08-14 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1.3 |  |  | 통합테스트 시정조치 |  |  |  | 30 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-08-15 | 2021-08-15 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1.3.1 | [6 empty] | 100 | 0% | 0% | 0 | 0 | 0 |  |  | 2021-08-15 | 2021-08-15 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
계획 입력 = MIN([계획 입력, row below]:P287)
계획 입력 = MAX([계획 입력, row below]:Q287)
상세일정계획서 = NETWORKDAYS([계획 입력],[계획 입력])

## 진척관리보고서
상세일정계획 및 진척관리
1. 진척 점검일자 입력 |  | 2021-05-07 |  | 월별진척율 | 계획진척율 | 실적진척율 | 주별일자 | 계획진척율 | 실적진척율 | 계획대비 실적율
|  |  |  | 2021-01-23 | 2.16% | 2.16% | 2021-01-02 | 0.36% | 0.36% | 100%
|  |  |  | 2021-02-27 | 10.1% | 10.1% | 2021-01-09 | 0.96% | 0.96% | 100%
2. 전체 진행 현황 |  |  |  | 2021-03-27 | 24.5% | 24.5% | 2021-01-16 | 1.56% | 1.56% | 100%
| ㅇ 계획율(누적) | 57.86% |  | 2021-04-24 | 38% | 38% | 2021-01-23 | 2.16% | 2.16% | 100%
| ㅇ 실적(누적) | 44.39% |  | 2021-05-29 | 55.6% | 55.6% | 2021-01-30 | 3.57% | 3.57% | 100%
| ㅇ 계획 대비 실적 | 76.72% |  | 2021-06-26 | 78% | 78% | 2021-02-06 | 4.7% | 4.7% | 100%
|  |  |  | 2021-07-24 | 87.4% | 87.4% | 2021-02-13 | 6.8% | 6.8% | 100%
|  |  |  | 2021-08-28 | 0% | 0% | 2021-02-20 | 8.9% | 8.9% | 100%
3. 단계별 진행 현황 | [6 empty] | 2021-02-27 | 10.1% | 10.1% | 100%
구분 |  | 가중치 | 누적계획율 | 누적실적율 | 실적율 | 비고 | 2021-03-06 | 12.4% | 12.4% | 100%
A.0 프로젝트 관리 |  | 10 | 54.23% | 34% | 62.7% |  | 2021-03-13 | 15.3% | 15.3% | 100%
| A.0.1 착수/계획 | 30 | 100% | 60% | 60% |  | 2021-03-20 | 20.1% | 20.1% | 100%
| A.0.2 실행 | 40 | 60.56% | 40% | 66.05% |  | 2021-03-27 | 24.5% | 24.5% | 100%
| A.0.3 프로젝트 종료 | 30 | 0% | 0% |  |  | 2021-04-03 | 28.7% | 28.7% | 100%
A.1 프로젝트 수행 (Graphic) |  | 20 | 63.38% | 52.02% | 82.09% |  | 2021-04-10 | 30.4% | 30.4% | 100%
| A.1.1 캐릭터 | 60 | 100% | 83.38% | 83.38% |  | 2021-04-17 | 33% | 33% | 100%
| A.1.2 배경 | 40 | 8.448% | 5% | 59.18% |  | 2021-04-24 | 38% | 38% | 100%
| #REF! | #REF! | #REF! | #REF! | #REF! |  | 2021-05-01 | 40.4% | 40.4% | 100%
A.2 프로젝트 수행 (Client) |  | 20 | 73.2% | 40% | 54.65% |  | 2021-05-08 | 45% | 45% | 100%
| A.2.1 캐릭터 동작 | 20 | 100% | 100% | 100% |  | 2021-05-15 | 50% | 50% | 100%
| A.2.2 캐릭터 상태 | 20 | 100% | 100% | 100% |  | 2021-05-22 | 53.8% | 53.8% | 100%
A.3 프로젝트 수행 (Server) |  | 20 | 61.25% | 68.12% | 111.2% |  | 2021-05-29 | 55.6% | 55.6% | 100%
| A.3.1 클라이언트 기능 동기화 | 25 | 100% | 87.5% | 87.5% |  | 2021-06-05 | 62.4% | 62.4% | 100%
| A.3.2 서버 기능 | 25 | 100% | 100% | 100% |  | 2021-06-12 | 70% | 70% | 100%
A.4 프로젝트 수행 (Animation) |  | 20 | 64.37% | 44.8% | 69.59% |  | 2021-06-19 | 73.4% | 73.4% | 100%
| A.4.1 리깅 | 40 | 100% | 50% | 50% |  | 2021-06-26 | 78% | 78% | 100%
| A.4.2 애니메이션 | 40 | 60.94% | 50% | 82.05% |  | 2021-07-03 | 80% | 80% | 100%
A.5 테스트 |  | 10 | 0% | 0% |  |  | 2021-07-10 | 82.4% | 82.4% | 100%
| A.5.1 통합테스트 | 100 | 0% | 0% |  |  | 2021-07-17 | 85.3% | 85.3% | 100%
| #REF! | #REF! | #REF! | #REF! | #REF! |  | 2021-07-24 | 87.4% | 87.4% | 100%
| #REF! | #REF! | #REF! | #REF! | #REF! |  | 2021-07-31 | 88.1% | 88.1% | 100%
| #REF! | #REF! | #REF! | #REF! | #REF! |  | 2021-08-07
#REF! |  | #REF! | #REF! | #REF! | #REF! |  | 2021-08-14
| #REF! | #REF! | #REF! | #REF! | #REF! |  | 2021-08-21
| #REF! | #REF! | #REF! | #REF! | #REF! |  | 2021-08-28
#REF! |  | #REF! | #REF! | #REF! | #REF! |  | 2021-09-04 | 90.6% | 90.6% | 100%
|  | 50 | 0% | 0% | 0% |  | 2021-09-11 | 92.52% | 92.52% | 100%
|  | 0 | 0% | 0% | 0% |  | 2021-09-18 | 94.44% | 94.44% | 100%
|  | 50 | 0% | 0% | 0% |  | 2021-09-25 | 96.36% | 96.36% | 100%
계 |  |  | 57.86% | 44.39% | 76.72% |  | 2021-10-02
2021-10-09
2021-10-16
2021-10-23
[7 empty] | 2021-10-30 | 98.28% | 98.28% | 100%
[7 empty] | 2021-11-06 | 100.2% | 100.2% | 100%
[7 empty] | 2021-11-13 | 101% | 101% | 100%
[7 empty] | 2021-11-20 | 101.9% | 101.9% | 100%
[7 empty] | 2021-11-27 | 102.8% | 102.8% | 100%
[7 empty] | 2021-12-04 | 103.7% | 103.7% | 100%
4. 단계별 진행 현황 (그래프)
서클 오픈(3/5)
메일 오픈(2/5)

## 공휴일
2021-02-11 | 설날연휴
2021-02-12 | 설날연휴
2021-02-13 | 설날연휴
2021-03-01 | 삼일절
2021-03-02 | 개강일
2021-04-20 | 중간고사 시작일
2021-04-26 | 중간고사 마감일
2021-05-05 | 어린이날
2021-05-19 | 부처님오신날
2021-06-06 | 현충일
2021-06-07 | 대체공휴일
2021-06-08 | 기말고사 시작일
2021-06-21 | 기말고사 마감일
2021-06-22 | 하계방학 시작
2021-08-15 | 광복절
2021-08-16 | 대체공휴일
2021-09-01 | 개강일
2021-09-20 | 추석연휴
2021-09-21 | 추석연휴
2021-09-22 | 추석연휴
2021-10-03 | 개천절
2021-10-09 | 한글날
2021-10-13 | 산업기술대전
2021-10-14